## Sheet1
| Condition | Start | Completion
Underframe | Good
Brake gear overhaul | Ok | 2023-07-01 | 2024-03-01
Draw hook testing |  | 2023-08-01 | 2023-09-01
Ultrsonic axle testing |  | 2023-08-01 | 2023-09-01
Extension design work |  | 2023-07-01 | 2023-10-01
Extension to frame |  | 2023-12-01 | 2024-04-01
Upper body
Teak body panel replacement | Poor | 2023-12-01
Upper side panels rrefurbishment | reasonable | 2023-09-01 | 2024-10-01
End panels refurbishment | Good in places | 2023-09-01 | 2024-10-01
Door refurbishment | Poor | 2023-10-01 | 2024-07-01
Window replacement | unknown | 2023-10-01 | 2024-07-01
Canvas Roof covering | Poor | 2024-12-01 | 2025-03-01
Exterior final painting | None | 2025-01-01 | 2025-04-01
Steam heating fitting | None present | 2024-11-01 | 2025-03-01
Floor covering | None present | 2025-03-01 | 2025-04-01
Seating | Some | 2023-09-01 | 2025-03-01
Internal fixtures | Refurbishment | 2024-10-01 | 2025-03-01
Remounting on body | Body lift | 2024-04-01